## SPM ASSIGNMENT 4
WBS LEVEL | TASK ID | TASK NAME | DESCRIPTION
1 | 1 | Healthful Plates Project | The overall project is to develop the Healthful Plates application.
2 | 2 | Initiation | Start and define the project.
3 | 2.1 | Project Objectives | Define project objectives and success criteria.
3 | 2.2 | Stakeholder Identification | Identify stakeholders and determine their needs.
3 | 2.3 | Feasibility Study | Analyze the technical and financial feasibility of the project.
2 | 3 | Planning | Plan tasks and resources for project execution.
3 | 3.1 | Requirements Gathering | Conduct detailed requirements gathering for all features.
3 | 3.2 | Risk Assessment | Identify potential risks and develop mitigation strategies.
3 | 3.3 | Project Schedule | Define project timelines and key milestones.
2 | 4 | Execution | Develop, build, and implement the Healthful Plates platform.
3 | 4.1 | System Design | Create system architecture, database design, and UI/UX designs.
4 | 4.1.1 | Architecture Design | Design high-level and low-level system architecture.
4 | 4.1.2 | Database Design | Define data structures and schema for the database.
4 | 4.1.3 | UI/UX Design | Develop wireframes, prototypes, and style guidelines.
3 | 4.2 | Development | Code and build individual modules and components.
4 | 4.2.1 | Module Development | Develop frontend and backend modules for recipes, carts, and user management.
4 | 4.2.2 | Code Review | Review code for quality and adherence to standards.
3 | 4.3 | Testing | Conduct various levels of testing to ensure platform stability and usability.
4 | 4.3.1 | Unit Testing | Test individual components such as forms and API endpoints.
4 | 4.3.2 | Integration Testing | Test interactions between frontend and backend components.
4 | 4.3.3 | System Testing | Test the entire system for end-to-end functionality.
4 | 4.3.4 | User Acceptance Testing (UAT) | Validate the system with test users to ensure it meets requirements.
2 | 5 | Monitoring & Control | Ensure the project remains on track and within scope.
3 | 5.1 | Scope Management | Monitor changes in project requirements and scope.
3 | 5.2 | Schedule Tracking | Track progress against the project schedule.
3 | 5.3 | Risk Management | Monitor and mitigate project risks.
2 | 6 | Closing | Finalize and close the Healthful Plates project.
3 | 6.1 | Final Testing | Ensure all testing is complete and quality standards are met.
3 | 6.2 | Documentation | Complete project documentation, including user manuals and technical references.
3 | 6.3 | User Training | Train users on how to use the platform and provide initial support.